## Dashboard
LYW PROJECT — SUBMITTAL TRACKING DASHBOARD
Generated 03 Jul 2026 07:56 ¦ Data source: ACC Submittals API ¦ Total: 420 submittals ¦ 88% Approved
Total Submittals |  | Approved |  |  | Pending (No Response) | Revise & Resubmit
420 |  | 368 |  |  | 37 | 14
SUBMITTALS BY DISCIPLINE
Discipline | Total | Approved | Pending | Resubmit | % Approved
MEP | 242 | 212 | 18 | 11 | 88%
Structural | 90 | 76 | 14 | 0 | 84%
Architectural | 87 | 79 | 5 | 3 | 91%
BIM | 1 | 1 | 0 | 0 | 100%
⚠️ PENDING > 90 DAYS — 6 ITEMS — URGENT FOLLOW-UP REQUIRED
ID | Title |  |  |  | Discipline | Days Pending
018 | level 1 Substation Sprinkler and Smoke Detector Layout |  |  |  | MEP | 266
006 | shop drawing submission of SANITARY SYSTEM DETAILS OF GREASE TRAP |  |  |  | MEP | 251
006 | Method of Statement for Electrical Installation |  |  |  | MEP | 221
006 | Method Statement for PU grouting Works |  |  |  | CS | 141
055 | 4th to 6th storey plumbing system |  |  |  | MEP | 132
059 | ACMV Control Panel Locations |  |  |  | MEP | 113
🔴 REVISE & RESUBMIT — 14 ITEMS — ACTION REQUIRED
ID | Title |  |  |  | Discipline | Comment
015 | RFA-AR-DWG-015 1st Sty Wall Setting Out Canteen Area |  |  |  | AR | IDA have few comments on other items, column size, baffle ceiling height, bollard spacing
013 | RFA-AR-MAT-013 ESS, MDF Rm & LT-CSR Rm Fire Rated Doors |  |  |  | AR
003 | RFA-AR-MS-003 AAC Wall Panel with Steel Lintel & Stiffener Installation Works |  |  |  | AR | IDA: Approved with Comments / TCS: Revised & Resubmit
13 | Genset FAT Procedure and Testing Report Form |  |  |  | MEP
9 | Lighting Lux Level Simulation |  |  |  | MEP
033 | Tray and Trunking for ACMV (Indoor) |  |  |  | MEP
045 | Electrical Conduit and Accesories |  |  |  | MEP | Please refer to attachment for BCE comments.
048 | Electrical - PWD Toilet Standalone System |  |  |  | MEP | Please refer to comment of BCE reply.
095 | Private Water Meter |  |  |  | MEP | Noted on the change of brand from original proposed brand (Itron). during tender stage. No objection on the brand. Please also submit the other size o
096 | Lockable Tap |  |  |  | MEP | Please refer to the attachment
098 | EPS |  |  |  | MEP | Refer to attachment.
106 | EMS |  |  |  | MEP
109 | CCTV |  |  |  | MEP | Refer to the attachment for comment.
114 | Domestic Water Booster and Transfer Pumps |  |  |  | MEP

## Summary
LYW PROJECT — SUBMITTAL STATUS REPORT
416 total submittals ¦ 2026-06-19 06:49
Total |  | ✅ Approved |  | ⏳ Pending |  | 🔴 Resubmit
416 |  | 358 |  | 46 |  | 12
⚠️ 8 pending submittals are over 90 days old — urgent follow-up needed
BY DISCIPLINE
Discipline | Total | Approved | Pending | Resubmit | % Approved
AR | 87 | 79 | 5 | 3 | 91%
BIM | 1 | 1 | 0 | 0 | 100%
CS | 89 | 72 | 17 | 0 | 81%
MEP | 239 | 206 | 24 | 9 | 86%

## ARC
ARC SUBMITTALS
87 total ¦ ✅79 Approved ¦ ⏳5 Pending ¦ 🔴3 Resubmit
ID | Title | Spec | Response Status | Priority | Required Approval Date | Sent to Review | Days Pending | Comment
003 | RFA-AR-MS-003 AAC Wall Panel with Steel Lintel & S | RFA-AR-MS | Revise and resubmit | High | 2025-11-10 | 2025-10-27 |  | IDA: Approved with Comments / TCS: Revised & Resubmit
013 | RFA-AR-MAT-013 ESS, MDF Rm & LT-CSR Rm Fire Rated | RFA-AR-MAT | Revise and resubmit | Normal | 2025-11-14 | 2025-10-31
015 | RFA-AR-DWG-015 1st Sty Wall Setting Out Canteen Ar | RFA-AR-DWG | Revise and resubmit | High | 2025-11-28 | 2026-04-27 |  | IDA have few comments on other items, column size, baffle ceiling height, bollard spacing
002 | RFA-AR-MS-002 RWDP Installation Works | RFA-AR-MS | Pending (No Response Yet) | Normal | 2025-10-17 | 2026-04-29 | 50
011 | RFA-AR-MS-011 Roller Shutter Installation Works | RFA-AR-MS | Pending (No Response Yet) | High | 2026-05-15 | 2026-05-08 | 41
046 | RFA-AR-DWG-046 Column Guard, Wheel Stopper, Humps, | RFA-AR-DWG | Pending (No Response Yet) | Normal | 2026-06-08 | 2026-05-25 | 24
027 | RFA-AR-MAT-027 Engineered Timber for TImber Seats | RFA-AR-MAT | Pending (No Response Yet) | High | 2026-06-19 | 2026-06-12 | 6
028 | RFA-AR-MAT-028 Bicycle Rack & Driveway Carpark Acc | RFA-AR-MAT | Pending (No Response Yet) | High | 2026-06-22 | 2026-06-15 | 4
033 | RFA-AR-DWG-033 4th Sty Wall Setting Out (Factory U | RFA-AR-DWG | Approved | High | 2026-03-26 | 2026-03-12
009 | RFA-AR-DWG-009 ESS Aluminium Louvres and Doors | RFA-AR-DWG | Approved | High | 2025-11-07 | 2026-02-13
017 | RFA-AR-MAT-017 Floor & Wall Tiles (Malford) | RFA-AR-MAT | Approved | High | 2026-01-22 | 2026-01-22
019 | RFA-AR-MAT-019 Toilet - Fixed Mirrors | RFA-AR-MAT | Approved | High | 2026-01-30 | 2026-01-30
020 | RFA-AR-MAT-020 Solid Surface & Toilet Cubicle (Eco | RFA-AR-MAT | Approved | High | 2026-02-07 | 2026-01-31
034 | RFA-AR-DWG-034 Typical Riser Cleaning Eyes Access | RFA-AR-DWG | Approved | High | 2026-04-09 | 2026-03-26
001 | RFA-AR-DWG-001 Waterproofing to Lift Wall | RFA-AR-DWG | Approved | High | 2025-08-06 | 2025-07-30
006 | RFA-AR-MAT-006 Lightweight Concrete Panel (Welmate | RFA-AR-MAT | Approved | Normal | 2025-08-16 | 2025-08-12
010 | RFA-AR-MAT-010 Floor Hardener (ABA 315L) | RFA-AR-MAT | Approved | High | 2025-09-30 | 2025-09-23
013 | RFA-AR-DWG-013 Roller Shutters (2HR Fire Rated wit | RFA-AR-DWG | Approved | Normal | 2025-11-27 | 2025-11-19
016 | RFA-AR-DWG-016 Fire Curtains (2nd Sty - 9th Sty) | RFA-AR-DWG | Approved | High | 2025-12-05 | 2025-11-22
011 | RFA-AR-MAT-011 ESS Aluminium Works (Hong Xing) | RFA-AR-MAT | Approved | High | 2025-11-08 | 2025-11-17
001 | Method Statement for Anti-Termite Soil Treatment | RFA-AR-MS | Approved | High | 2025-07-11 | 2025-06-27
003 | RFA-AR-MAT-003 Glass Block & PC Vent Block for ESS | RFA-AR-MAT | Approved | Normal | 2025-08-11 | 2025-07-28
001 | RFA-AR-MAT-001 Pre-Packed Materials | RFA-AR-MAT | Approved | Normal | 2025-08-07 | 2025-07-24
008 | RFA-AR-MAT-008 Floor Hardener (STO Crete) | RFA-AR-MAT | Approved | High | 2025-08-19 | 2025-08-12
015 | RFA-AR-MAT-015 Ironmongery Schedule, Cut Sheet and | RFA-AR-MAT | Approved | High | 2025-12-03 | 2025-12-19
005 | RFA-AR-MAT-005 Waterproofing Works (Hitchins - Pro | RFA-AR-MAT | Approved | High | 2025-08-08 | 2025-08-01
002 | RFA-AR-MAT-002 Waterproofing Lift Pit Wall (Prower | RFA-AR-MAT | Approved | High | 2025-07-29 | 2025-07-28
004 | RFA-AR-MAT-004 RWDP Drainage System (UV Sytem) | RFA-AR-MAT | Approved | Normal | 2025-08-12 | 2025-07-29
022 | RFA-AR-DWG-022 2nd -10th Sty Aluminium & Glazing W | RFA-AR-DWG | Approved with comments | High | 2025-12-30 | 2025-12-16
005 | RFA-AR-MS-005 MOS for Floor Screeding, Wall & Floo | RFA-AR-MS | Approved | High | 2026-01-02 | 2025-12-18
023 | RFA-AR-DWG-023 1st Sty Factory Unit Wall Setting O | RFA-AR-DWG | Approved | High | 2025-12-23 | 2025-12-16
009 | RFA-AR-MAT-009 Concealed Conduit Pipes (Internal D | RFA-AR-MAT | Approved | Normal | 2025-08-29 | 2025-08-22
004 | RFA-AR-DWG-004 Vehicular Ramp FFL & Groove Line Se | RFA-AR-DWG | Approved | High | 2025-10-07 | 2025-12-04
007 | RFA-AR-MAT-007 Sanitary Wares & Fittings (Rigel Te | RFA-AR-MAT | Approved with comments | Normal | 2025-08-18 | 2025-12-05
010 | RFA-AR-DWG-010 ESS, MDF Rm & LT-CSR Rm Fire Rated | RFA-AR-DWG | Approved | High | 2025-11-14 | 2025-12-02
025 | RFA-AR-MAT-025 Linear & Baffle Ceiling for 1st Sty | RFA-AR-MAT | Approved with comments | High | 2026-05-21 | 2026-05-14 |  | IDA: Approved. BSD: Approved with comments, to ensure 60% of ceiling works will use 4ticks SGBP
002 | RFA-AR-DWG-002 Waterproofing Works (1st Sty to 9th | RFA-AR-DWG | Approved with comments | High | 2025-08-29 | 2025-09-22 |  | To extend WP application to 300mm instead of 100mm from water level
018 | RFA-AR-DWG-018 Aluminium Louvre & Door 1st Sty LT- | RFA-AR-DWG | Approved | High | 2025-12-16 | 2025-12-02
014 | RFA-AR-MAT-014 Roller Shutters (FR & Non FR) & Fir | RFA-AR-MAT | Approved | High | 2025-11-17 | 2025-11-03
011 | RFA-AR-DWG-011 ESS FR Roller Shutter, Trap Door & | RFA-AR-DWG | Approved with comments | High | 2025-11-18 | 2025-11-07
008 | RFA-AR-DWG-008 1st Sty Wall Setting Out Factory Un | RFA-AR-DWG | Approved with comments | High | 2025-11-06 | 2025-10-23
012 | RFA-AR-MAT-012 Steel Lintel & Stiffener (Leet Stee | RFA-AR-MAT | Approved with comments | High | 2025-11-08 | 2025-10-25
012 | RFA-AR-DWG-012 1st Sty Wall Setting Out Factory Un | RFA-AR-DWG | Approved with comments | High | 2025-11-20 | 2025-11-06
019 | RFA-AR-DWG-019 Roller Shutters for 1st Sty and 10t | RFA-AR-DWG | Approved with comments | High | 2025-12-12 | 2025-12-05
020 | RFA-AR-DWG-020 Aluminiun Fins - External Facade | RFA-AR-DWG | Approved with comments | High | 2025-12-19 | 2025-12-05
004 | RFA-AR-MS-004 MOS for Plaster & Skim Coat Works | RFA-AR-MS | Approved | High | 2026-01-02 | 2025-12-18
016 | RFA-AR-MAT-016 Waterproofing for External Wall Joi | RFA-AR-MAT | Approved | High | 2026-01-22 | 2026-01-15
028 | RFA-AR-DWG-028 3rd Sty Wall Setting Out (Factory U | RFA-AR-DWG | Approved | High | 2026-03-06 | 2026-02-20
025 | RFA-AR-DWG-025 2nd Sty Wall Setting Out (Factory U | RFA-AR-DWG | Approved | High | 2026-02-07 | 2026-02-10
006 | RFA-AR-MS-006 Aluminium, Glazing, Shop Front, Louv | RFA-AR-MS | Approved | Normal | 2026-02-27 | 2026-02-13
007 | RFA-AR-MS-007 Timber & Metal Door Installation Wor | RFA-AR-MS | Approved | High | 2026-02-27 | 2026-02-13
003 | RFA-AR-DWG-003 Rain Water Drainage System | RFA-AR-DWG | Approved | High | 2025-09-01 | 2026-05-15
026 | RFA-AR-MAT-026 Insulation Board for Waterproofing | RFA-AR-MAT | Approved | High | 2026-05-22 | 2026-05-15
043 | RFA-AR-DWG-043 Ceiling Plan for 1st Sty Canteen, F | RFA-AR-DWG | Approved | High | 2026-05-06 | 2026-05-25
044 | RFA-AR-DWG-044 1st Sty FFL-5 Metal Door FMD18B (Up | RFA-AR-DWG | Approved | High | 2026-05-06 | 2026-04-29
029 | RFA-AR-DWG-029 1st Sty Non-Typical Toilet Tile Set | RFA-AR-DWG | Approved | High | 2026-03-06 | 2026-03-27
023 | RFA-AR-MAT-023 Ceiling Works for FCC Rm, Lift Lobb | RFA-AR-MAT | Approved | High | 2026-04-25 | 2026-04-18
017 | RFA-AR-DWG-017 ESS Wall Setting Out | RFA-AR-DWG | Approved | High | 2025-12-08 | 2026-02-27
040 | RFA-AR-DWG-040 Waterproofing Works (2nd Sty to 10t | RFA-AR-DWG | Approved | Normal | 2026-04-22 | 2026-04-15
009 | RFA-AR-MS-009 Toilet Mirror Installation Works | RFA-AR-MS | Approved | High | 2026-04-27 | 2026-04-20
035 | RFA-AR-DWG-035 Bin Compactor & Bin Centre Tile Set | RFA-AR-DWG | Approved | High | 2026-04-10 | 2026-04-02
032 | RFA-AR-DWG-032 Typical Factory Units Meter Compart | RFA-AR-DWG | Approved | High | 2026-03-17 | 2026-03-10
012 | RFA-AR-MS-012 External Wall Painting Works | RFA-AR-MS | Approved | High | 2026-06-16 | 2026-06-09
026 | RFA-AR-DWG-026 2nd-9th Sty Typical Lift Lobbies Wa | RFA-AR-DWG | Approved with comments | High | 2026-02-12 | 2026-05-05
027 | RFA-AR-DWG-027 10th Sty & Roof Waterproofing Works | RFA-AR-DWG | Approved with comments | High | 2026-02-19 | 2026-04-15
021 | RFA-AR-MAT-021 Bin Compactor (SLS Engineering) | RFA-AR-MAT | Approved | High | 2026-04-08 | 2026-03-25
021 | RFA-AR-DWG-021 Metal Doors - 1st to 10th Sty | RFA-AR-DWG | Approved | High | 2025-12-29 | 2026-03-10
014 | RFA-AR-DWG-014 1st Sty Aluminium & Glazing Works | RFA-AR-DWG | Approved | High | 2025-11-28 | 2026-02-28
031 | RFA-AR-DWG-031 1st Sty Updated Bin Centre Roller S | RFA-AR-DWG | Approved | High | 2026-03-17 | 2026-03-10
041 | RFA-AR-DWG-041 2nd to 9th Sty Typical Risers Wall | RFA-AR-DWG | Approved | High | 2026-05-04 | 2026-04-27
005 | RFA-AR-DWG-005 1st Sty Typical Toilet Tile Setting | RFA-AR-DWG | Approved | Normal | 2025-10-13 | 2026-03-27
007 | RFA-AR-DWG-007 2nd Sty Typical Toilet Tile Setting | RFA-AR-DWG | Approved | Normal | 2025-10-16 | 2026-03-27
030 | RFA-AR-DWG-030 2nd - 10th Sty Non-Typical Toilet T | RFA-AR-DWG | Approved | High | 2026-03-06 | 2026-03-27
037 | RFA-AR-DWG-037 Toilet Cubicle & Solid Surface Top | RFA-AR-DWG | Approved with comments | High | 2026-04-16 | 2026-04-09
010 | RFA-AR-MS-010 Toilet & Canteen Solid Surface Vanit | RFA-AR-MS | Approved | High | 2026-04-27 | 2026-04-20
024 | RFA-AR-MAT-024 Soap Dispenser for 1st Sty Canteen | RFA-AR-MAT | Approved with comments | High | 2026-04-27 | 2026-04-20 |  | SBPL have capture the comments and indicated in RFA-AR-DWG-006 R5 shop drawing submissions (Canteen WSO&TSO). SBPL shared the dwgs to BSD to clarify, BSD have no objections.
006 | RFA-AR-DWG-006 1st Sty Canteen Toilet & FCC Rm Til | RFA-AR-DWG | Approved | Normal | 2025-10-14 | 2026-04-28
008 | RFA-AR-MS-008 Ceiling Installation Works | RFA-AR-MS | Approved | High | 2026-04-22 | 2026-04-15
024 | RFA-AR-DWG-024 1st Sty Lift Lobbies Wall Setting O | RFA-AR-DWG | Approved with comments | High | 2026-01-20 | 2026-05-05
039 | RFA-AR-DWG-039 Aluminium Screen & Column Cladding | RFA-AR-DWG | Approved | High | 2026-04-21 | 2026-04-29
042 | RFA-AR-DWG-042 1st Sty Shop Front Glass Door (8mm | RFA-AR-DWG | Approved with comments | High | 2026-05-06 | 2026-04-29
036 | RFA-AR-DWG-036 Ceiling Works for Typical Toilets ( | RFA-AR-DWG | Approved | High | 2026-04-14 | 2026-05-14
022 | RFA-AR-MAT-022 Ceiling Works for Typical Toilet Fa | RFA-AR-MAT | Approved | High | 2026-04-14 | 2026-04-18
047 | RFA-AR-DWG-047 10th Sty Wall Setting Out (Factory | RFA-AR-DWG | Approved | High | 2026-06-02 | 2026-05-26
045 | RFA-AR-DWG-045 Additional Canopy for ESS & MDF Rm | RFA-AR-DWG | Approved | High | 2026-05-28 | 2026-05-21
018 | RFA-AR-MAT-018 Painting Works (T3 Intl) | RFA-AR-MAT | Approved | Normal | 2026-01-23 | 2026-06-10
038 | RFA-AR-DWG-038 Aluminium Downhang & Vertical Louvr | RFA-AR-DWG | Approved | High | 2026-04-21 | 2026-05-28

## BIM
BIM SUBMITTALS
1 total ¦ ✅1 Approved ¦ ⏳0 Pending ¦ 🔴0 Resubmit
ID | Title | Spec | Response Status | Priority | Required Approval Date | Sent to Review | Days Pending | Comment
001 | Submission of BIM Execution Plan | RFA-BIM-BEP | Approved | High | 2025-12-10 | 2025-11-26

## STR
STR SUBMITTALS
89 total ¦ ✅72 Approved ¦ ⏳17 Pending ¦ 🔴0 Resubmit
ID | Title | Spec | Response Status | Priority | Required Approval Date | Sent to Review | Days Pending | Comment
001 | Scenario of Pilecap Construction & Concrete Grade | RFA-CS-GN | Pending (No Response Yet) | High | 2025-07-14 | 2025-06-30 | 353
006 | Method Statement for PU grouting Works | RFA-CS-MS | Pending (No Response Yet) | High | 2026-02-19 | 2026-02-12 | 127
1 | M12 and M16 Bolt test report for Steel structure | RFA-CS-RPT | Pending (No Response Yet) | High |  | 2026-04-16 | 64
026 | Railing Shop drawing at L1 Entrance | RFA-CS-DWG | Pending (No Response Yet) | Normal | 2026-02-12 | 2026-04-30 | 50
033 | Metal Staircase 1 and Handrail Shop Drawing | RFA-CS-DWG | Pending (No Response Yet) | High |  | 2026-05-14 | 36
034 | Metal Staircase 4 and Handrail Shop Drawing | RFA-CS-DWG | Pending (No Response Yet) | High |  | 2026-05-14 | 36
039 | Metal Staircase 3 and Handrail Shop Drawing | RFA-CS-DWG | Pending (No Response Yet) | High |  | 2026-05-14 | 36
038 | Catladder and Hatch door Shop drawing | RFA-CS-DWG | Pending (No Response Yet) | High |  | 2026-05-15 | 35
044 | Metal Staircase 5 and Handrail Shop Drawing | RFA-CS-DWG | Pending (No Response Yet) | High | 2026-06-01 | 2026-05-19 | 31
045 | Metail Staircase 6 and Handrail Shop Drawing (At r | RFA-CS-DWG | Pending (No Response Yet) | High | 2026-06-01 | 2026-05-19 | 31
021 | Expanded Mesh for M&E Riser | RFA-CS-MAT | Pending (No Response Yet) | High | 2026-06-04 | 2026-05-22 | 27
051 | Shop Drawing for Steel Roof | RFA-CS-DWG | Pending (No Response Yet) | High | 2026-06-07 | 2026-06-09 | 10
052 | L10 PT Shopdrawings | RFA-CS-DWG | Pending (No Response Yet) | High | 2026-06-17 | 2026-06-16 | 3
055 | L10 Ramp PT Shop drawings | RFA-CS-DWG | Pending (No Response Yet) | High | 2026-06-29 | 2026-06-16 | 3
056 | RFA-CS-DWG-056-Hollow Core Slab Shopdrawing (L10-L | RFA-CS-DWG | Pending (No Response Yet) | High | 2026-06-28 | 2026-06-18 | 0
053 | Steel Support for Toilet Solid Surface | RFA-CS-DWG | Pending (No Response Yet) | High | 2026-06-09 | 2026-06-19 | 0
020 | Steel Fiber for Concrete (Continental Steel) | RFA-CS-MAT | Pending (No Response Yet) | High | 2026-04-17 | 2026-06-19 | 0
004 | Concrete Curing Compound | RFA-CS-MAT | Approved | High | 2025-07-16 | 2025-07-02
003 | Concrete Design Mix By Topmix Supplier | RFA-CS-MAT | Approved with comments | High | 2025-06-10 | 2025-06-30
005 | Non-Shrink Grout for Concrete Repair | RFA-CS-MAT | Approved with comments | High | 2025-07-23 | 2025-07-09
015 | Shopdrawings for Precast Sump | RFA-CS-DWG | Approved with comments | High | 2025-11-24 | 2025-11-17 |  | SBPL noted on the comments
011 | Level 1 to Level 2 Ramp PT Shop drawings | RFA-CS-DWG | Approved | High | 2025-10-14 | 2025-11-21
006 | Concrete Body Plan of Level 1 | RFA-CS-DWG | Approved with comments | High | 2025-09-23 | 2025-11-17
024 | Level 4 PT Shopdrawings | RFA-CS-DWG | Approved with comments | High | 2026-02-09 | 2026-02-24 |  | SBPL noted on the comments
002 | Concrete Design Mix By Sinmix Supplier | RFA-CS-MAT | Approved | High | 2025-06-09 | 2025-06-30
003 | Column Prefab Shopdrawing | RFA-CS-DWG | Approved with comments | High | 2025-08-16 | 2025-08-02
001 | Precast U-Drain Shopdrawing | RFA-CS-DWG | Approved with comments | High | 2025-08-01 | 2025-07-18 |  | No comment for drain section details. please note we are still pending for PUB DC and BP clearances for detention drain. please highlight for any deviation from prelim/approved drawings
006 | RFA-CS-MAT-006 - Waterproof Admixture Concrete Des | RFA-CS-MAT | Approved with comments | High | 2025-08-22 | 2025-08-17 |  | SBPL noted on the comments
007 | Scanfiber Materials for 1st Storey Driveway Slab | RFA-CS-MAT | Approved with comments | High | 2025-08-22 | 2025-08-08 |  | SBPL noted on the comments
009 | Concrete Design Mix of YTL | RFA-CS-MAT | Approved with comments | Normal | 2025-09-30 | 2025-09-16 |  | SBPL noted on the comments
2 | Design Calculation and Drawings for Rectangular Co | RFA-CS-PE | Approved with comments | High | 2025-09-29 | 2025-09-22 |  | SBPL noted on the comments
011 | RFA-CS-MAT-011-Expansion Joint Fillerboard for Dou | RFA-CS-MAT | Approved | High | 2025-10-01 | 2025-10-09
3 | RFA-CS-PE-3-Design Calculation and Drawings for Li | RFA-CS-PE | Approved with comments | High | 2025-09-30 | 2025-09-23 |  | SBPL noted on the comments
4 | RFA-CS-PE-4-Design Calculation and Drawings for Ra | RFA-CS-PE | Approved with comments | High | 2025-10-06 | 2025-09-29 |  | SBPL noted on the comments
1 | Design Calculation and Drawings for Lift Wall Syst | RFA-CS-PE | Approved with comments | High | 2025-09-29 | 2025-09-22 |  | SBPL noted on the comments
008 | Concealed Conduit Pipe Materials | RFA-CS-MAT | Approved with comments | High | 2025-08-22 | 2025-08-15 |  | SBPL noted on the comments
002 | Concrete Body Plan of Water Tank & Substation | RFA-CS-DWG | Approved with comments | High | 2025-08-05 | 2025-08-26 |  | SBPL noted on the comments
005 | Hollow Core Slab Shopdrawing (L2 to L9) | RFA-CS-DWG | Approved with comments | High | 2025-09-16 | 2025-09-23 |  | SBPL noted on the comments
004 | L1 Concrete Body Plan Part Plan at Column C1 & C3 | RFA-CS-DWG | Approved with comments | High | 2025-09-02 | 2025-08-19 |  | SBPL noted on the comments
002 | Method of Statement for Pile Hacking & Pile Remedi | RFA-CS-MS | Approved | High | 2025-06-24 | 2025-06-19
003 | RFA-CS-MS-CS-Method Statement for Post Tension Wor | RFA-CS-MS | Approved with comments | High | 2025-09-30 | 2025-09-23 |  | SBPL noted on the comments
6 | Design Calculation for Tower Crane Tie Back | RFA-CS-PE | Approved | High | 2025-10-17 | 2025-10-03
004 | Method Statement for Concrete Repair Works | RFA-CS-MS | Approved | High | 2025-10-24 | 2025-10-17
5 | RFA-CS-PE-5-Design Calculation and Drawings for Ma | RFA-CS-PE | Approved with comments | High | 2025-10-06 | 2025-09-29 |  | SBPL noted on the comments
009 | Level 2 PT Shop drawings | RFA-CS-DWG | Approved with comments | High | 2025-10-10 | 2025-10-29 |  | SBPL noted on the comments
012 | Shop drawing for Precast U Drain for Detention Dra | RFA-CS-DWG | Approved with comments | High | 2025-10-24 | 2025-10-17
008 | Method Statement for Erection of Steel Staircase, | RFA-CS-MS | Approved with comments | High | 2026-06-04 | 2026-05-22
012 | Post Tension Works | RFA-CS-MAT | Approved with comments | High | 2025-09-30 | 2025-10-14 |  | SBPL noted on the comments
010 | Mechanical Coupler | RFA-CS-MAT | Approved | High | 2025-09-29 | 2025-11-08
016 | Level 2 PT Shop drawings (Rev 02) | RFA-CS-DWG | Approved with comments | High | 2025-11-22 | 2025-11-21 |  | SBPL noted on the comments
020.R1 | ESS Handrail, Guradrail and Grating Shop drawings_ | RFA-CS-DWG | Approved with comments | High |  | 2025-12-11
014 | Design Mix for Pan United Concrete | RFA-CS-MAT | Approved | High | 2025-11-30 | 2025-11-28
010.R2 | Shop drawings for Precast Staircase ST2_Rev.2(2025 | RFA-CS-DWG | Approved with comments | High | 2025-10-14 | 2026-02-13
017 | Grouting Cement for PT Works (Alternative for Engr | RFA-CS-MAT | Approved | High | 2025-12-23 | 2025-12-20
008 | RFA-CS-DWG-008-Concrete Body Plan of Level 2 | RFA-CS-DWG | Approved with comments | High | 2025-10-07 | 2025-11-26 |  | SBPL noted on the comments
015 | Design Mix for Alliance Concrete Singapore | RFA-CS-MAT | Approved | High | 2025-12-28 | 2025-12-15
016 | RFA-CS-MAT-016 - Waterproof Admixture Concrete Des | RFA-CS-MAT | Approved with comments | High | 2025-12-28 | 2025-12-15
007 | Concrete Body Plan of L1 to L2 Ramp and L2 to L3 R | RFA-CS-DWG | Approved with comments | High | 2025-10-07 | 2026-01-03 |  | SBPL noted on the comments
018 | Level 3 Ramp PT Shop drawings | RFA-CS-DWG | Approved with comments | High | 2025-12-08 | 2026-01-28
023 | Level 4 Ramp PT Shop drawings and PE calculation | RFA-CS-DWG | Approved with comments | High | 2026-01-27 | 2026-01-20 |  | SBPL noted with comments
017 | Level 3 PT Shop Drawings | RFA-CS-DWG | Approved with comments | High | 2025-12-08 | 2026-01-07
027 | Concrete Body Plan of L4 | RFA-CS-DWG | Approved with comments | High | 2026-03-03 | 2026-02-25
018 | Non-Shrink Grout for Structural Steel works | RFA-CS-MAT | Approved with comments | High |  | 2026-03-05
021 | Level 5 PT Shop drawings | RFA-CS-DWG | Approved with comments | High | 2025-12-17 | 2026-04-18
031 | Level 5 Ramp PT Shopdrawings | RFA-CS-DWG | Approved with comments | High | 2026-03-17 | 2026-03-06 |  | SBPL noted on the comments
014 | Hollow Core Slab Shopdrawing (L2 to L9) - Rev 04 | RFA-CS-DWG | Approved with comments | High | 2025-11-14 | 2026-01-23
019 | Staircase 2 railing shop drawings | RFA-CS-DWG | Approved with comments | High |  | 2026-03-27
019 | Proposed Mesh type(WM 50075) for Metal Staircase | RFA-CS-MAT | Approved with comments | High |  | 2026-04-14
032 | Grating Shop drawing | RFA-CS-DWG | Approved with comments | High |  | 2026-03-30
029 | Level 6 PT Shopdrawing | RFA-CS-DWG | Approved with comments | High | 2026-02-27 | 2026-04-10
002 | Inspection Test Plan for Structural Steelworks | RFA-CS-GN | Approved with comments | Normal |  | 2026-03-23
035 | Concrete Body Plan of L6 | RFA-CS-DWG | Approved with comments | High | 2026-04-09 | 2026-04-02 |  | SBPL noted on the comments
025 | Concrete Body Plan of L3 to L4 and L4 to L5 Ramp | RFA-CS-DWG | Approved with comments | High | 2026-02-06 | 2026-01-30
049 | Level 9 PT Shop drawings | RFA-CS-DWG | Approved with comments | High | 2026-06-07 | 2026-05-25
022 | Concrete Body Plan of Level 3 | RFA-CS-DWG | Approved with comments | High | 2025-12-28 | 2026-02-24
007 | Method Statement for Floor rectification works at | RFA-CS-MS | Approved with comments | High | 2026-04-02 | 2026-03-26 |  | SBPL noted on the comments
030 | Level 7 PT Shopdrawing | RFA-CS-DWG | Approved with comments | High | 2026-02-27 | 2026-04-18
028 | Concrete Body Plan for L5 | RFA-CS-DWG | Approved with comments | High | 2026-03-03 | 2026-04-18
037 | Concrete Body Plan of L7 | RFA-CS-DWG | Approved with comments | High | 2026-04-20 | 2026-04-13
041 | L8 PT Shop drawings | RFA-CS-DWG | Approved with comments | High | 2026-05-11 | 2026-04-29
043 | Concrete Body Plan L5 to L6 and L6 to L7 Ramp | RFA-CS-DWG | Approved with comments | High | 2026-05-21 | 2026-05-14
048 | Concrete Body Plan L7 to L8 ramp and L8 to L9 ramp | RFA-CS-DWG | Approved with comments | High | 2026-06-02 | 2026-05-20
036 | L6 Ramp PT Shopdrawings | RFA-CS-DWG | Approved with comments | High | 2026-04-13 | 2026-06-04
040 | Level 7 Ramp PT shopdrawings | RFA-CS-DWG | Approved with comments | High | 2026-04-24 | 2026-06-04
046 | Concrete Body Plan for L8 | RFA-CS-DWG | Approved with comments | High | 2026-06-02 | 2026-05-20
047 | Concrete Body Plan for L9 | RFA-CS-DWG | Approved with comments | High | 2026-06-02 | 2026-05-20
054 | L11 Roof PT Shop drawings | RFA-CS-DWG | Approved with comments | High | 2026-06-22 | 2026-06-09
042 | L8 Ramp PT Shop drawings | RFA-CS-DWG | Approved with comments | High | 2026-05-11 | 2026-06-04
050 | Level 9 Ramp PT Shop drawings | RFA-CS-DWG | Approved with comments | High | 2026-06-07 | 2026-05-25

## MEP
MEP SUBMITTALS
239 total ¦ ✅206 Approved ¦ ⏳24 Pending ¦ 🔴9 Resubmit
ID | Title | Spec | Response Status | Priority | Required Approval Date | Sent to Review | Days Pending | Comment
098 | EPS | RFA-MEP-MAT | Revise and resubmit | Normal | 2025-12-20 | 2025-12-06 |  | Refer to attachment.
109 | CCTV | RFA-MEP-MAT | Revise and resubmit | Normal | 2026-01-22 | 2026-01-08 |  | Refer to the attachment for comment.
045 | Electrical Conduit and Accesories | RFA-MEP-MAT | Revise and resubmit | High | 2025-11-08 | 2025-11-01 |  | Please refer to attachment for BCE comments.
096 | Lockable Tap | RFA-MEP-MAT | Revise and resubmit | Normal | 2025-12-13 | 2025-11-29 |  | Please refer to the attachment
095 | Private Water Meter | RFA-MEP-MAT | Revise and resubmit | Normal | 2025-12-13 | 2025-11-29 |  | Noted on the change of brand from original proposed brand (Itron). during tender stage. No objection on the brand. Please also submit the other size of water meter for approval.
048 | Electrical - PWD Toilet Standalone System | RFA-MEP-MAT | Revise and resubmit | High | 2025-11-10 | 2026-04-20 |  | Please refer to comment of BCE reply.
106 | EMS | RFA-MEP-MAT | Revise and resubmit | Normal | 2026-01-20 | 2026-01-06
114 | Domestic Water Booster and Transfer Pumps | RFA-MEP-MAT | Revise and resubmit | Normal | 2026-02-04 | 2026-06-15
9 | Lighting Lux Level Simulation | RFA-MEP-GN | Revise and resubmit | Normal | 2026-05-13 | 2026-04-29
018 | level 1 Substation Sprinkler and Smoke Detector La | RFA-MEP-DWG | Pending (No Response Yet) | High | 2025-10-23 | 2025-10-09 | 252
006 | shop drawing submission of SANITARY SYSTEM DETAIL | RFA-MEP-DWG | Pending (No Response Yet) | High | 2025-08-30 | 2025-10-24 | 237
004 | submission of underground combined services drawin | RFA-MEP-DWG | Pending (No Response Yet) | High | 2025-08-06 | 2025-11-06 | 224
006 | Method of Statement for Electrical Installati | RFA-MEP-MS | Pending (No Response Yet) | High | 2025-12-01 | 2025-11-24 | 206
055 | 4th to 6th storey plumbing system | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-03-07 | 2026-02-21 | 118
059 | ACMV Control Panel Locations | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-03-26 | 2026-03-12 | 99
066 | Lightning Protection System Plans ( level 2 to roo | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-04-27 | 2026-04-13 | 66
069 | Automatic Sprinkler / Hydrant System Schematic Di | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-04-29 | 2026-04-15 | 65
002 | Method of Statement for ACMV Installation | RFA-MEP-MS | Pending (No Response Yet) | High | 2025-11-27 | 2026-04-17 | 63
049 | ACMV installation details | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-02-02 | 2026-04-27 | 52
082 | Lighting Layout 10th Storey Plan | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-05-14 | 2026-04-30 | 50
084 | 3RD TO 6TH STOREY ELV LAYOUT | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-05-16 | 2026-05-02 | 48
089 | Proposed Dry Riser Location at FFL 2 and FFL 3 Typ | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-05-21 | 2026-05-14 | 35
088 | Electrical Main Single Line Diagrams | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-05-21 | 2026-06-08 | 10
11 | MSB 1 to 4 Single Line Diagram and Panel Arrangeme | RFA-MEP-GN | Pending (No Response Yet) | High | 2026-06-16 | 2026-06-09 | 10
12 | MSB_ Solar Single Line Diagram and Panel Arrangeme | RFA-MEP-GN | Pending (No Response Yet) | High | 2026-06-16 | 2026-06-09 | 10
093 | 1st Storey Lobby Reflected Ceiling Plan ( Lobby 1, | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-06-23 | 2026-06-09 | 10
094 | ircon Drain Pipe 3rd to 9th Storey Layout Plan & | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-06-25 | 2026-06-11 | 8
13 | Genset FAT Procedure and Testing Report Form | RFA-MEP-GN | Pending (No Response Yet) | High | 2026-06-17 | 2026-06-10 | 8
14 | MSB FAT Procedure and Test Report Form | RFA-MEP-GN | Pending (No Response Yet) | High | 2026-06-17 | 2026-06-10 | 8
095 | Aircon Drain Pipe 10th Storey Layout Plan & Secti | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-06-25 | 2026-06-11 | 8
031 | GI Trunking for ACMV Work | RFA-MEP-MAT | Pending (No Response Yet) | High | 2025-11-06 | 2026-06-15 | 3
033 | Tray and Trunking for ACMV (Indoor) | RFA-MEP-MAT | Pending (No Response Yet) | High | 2025-11-08 | 2026-06-15 | 3
096 | combined services drawings FCC room plan & elevat | RFA-MEP-DWG | Pending (No Response Yet) | High | 2026-07-03 | 2026-06-19 | 0
058 | Consumer Switch Room And Electrical Riser Layout | RFA-MEP-DWG | Approved with comments | High | 2026-03-20 | 2026-03-06
061 | Standby Hose Cabinet | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-11-16 |  | Please refer to attachment.
059 | Landing Valve | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-11-16
052 | 1st Storey ELV Layout | RFA-MEP-DWG | Approved with comments | High | 2026-02-16 | 2026-04-30
025 | Stainless steel water pipes and fittings | RFA-MEP-MAT | Approved | High | 2025-11-10 | 2025-10-27
021 | ALARM CHECK VALVE | RFA-MEP-MAT | Approved | Normal | 2025-10-30 | 2025-11-12
115 | Paint Material and Brand for P&S Services | RFA-MEP-MAT | Approved | Normal | 2026-02-04 | 2026-01-21
089 | EVC System Material | RFA-MEP-MAT | Approved with comments | Normal | 2025-12-12 | 2026-01-06 |  | Refer to attachment.
100 | Paint for Fire Protection Service | RFA-MEP-MAT | Approved | High | 2025-12-22 | 2026-01-22
099 | Floor Waste/Trap, Urinal Trap Cover and Anti Mosqu | RFA-MEP-MAT | Approved | Normal | 2025-12-22 | 2026-01-21
111 | Paint Material for DfMA Sprinkler Pipe | RFA-MEP-MAT | Approved | Normal | 2026-01-26 | 2026-01-12
107 | Sprinkler Pipe _DfMA | RFA-MEP-MAT | Approved with comments | Normal | 2026-01-22 | 2026-01-08 |  | Refer to attachment.
004 | Method of Statement for Fabrication and Install | RFA-MEP-MS | Approved with comments | High | 2025-11-27 | 2025-11-13
023 | GATE VALVE | RFA-MEP-MAT | Approved with comments | Normal | 2025-10-30 | 2025-11-10
076 | Hosereel Pump Set | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-11-16 |  | Please refer attachment for comment.
075 | Hydrant Pump Set | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-11-16 |  | No objection on the brand. Please submit pre-fab drawing for approval. Please submit control panel for approval. Please submit hydraulic calculation for approval of model. Please submit fuel tank size calculation and catalogue for approval. Please comply to SS575 instead of CP52 for calculation of f
074 | Sprinkler Pumpset | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-11-16 |  | No objection on the brand. Please submit pre-fab drawing for approval. Please submit control panel for approval. Please submit hydraulic calculation for approval of model. Please submit fuel tank size calculation and catalogue for approval. Please note the rated flow rate is 10L/min for jockey pump.
072 | Fire Stop Material for Fire Protection and Alarm S | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-11-16 |  | Please refer to attachment for BCE comment.
056 | Sprinkler Head | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-28 | 2025-11-15
057 | Breeching Inlet | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-28 | 2025-11-15 |  | Refer to attachment for comment.
094 | Ball Float Valve | RFA-MEP-MAT | Approved | Normal | 2025-12-13 | 2025-11-29
002 | material submission of ductile iron sanitary pipes | RFA-MEP-MAT | Approved | High | 2025-07-14 | 2025-06-30
007 | 1st storey U/G electrical pipes for earthing syste | RFA-MEP-DWG | Approved | High | 2025-09-08 | 2025-08-25
011 | Ductile Iron Inspection Chamber Cover & Frame | RFA-MEP-MAT | Approved | High | 2025-08-18 | 2025-08-04
040 | 1st storey combined services drawings | RFA-MEP-DWG | Approved with comments | High | 2026-01-06 | 2026-03-30
044 | MV-CO Sensor | RFA-MEP-MAT | Approved with comments | High | 2025-11-08 | 2025-11-01 |  | Please refer to the attachment for the comment.
088 | Electrical Switchboard and DB | RFA-MEP-MAT | Approved with comments | Normal | 2025-12-12 | 2025-11-28 |  | Please refer to attachment.
6 | ESS 1, 2 and MDF Rooms DB SLD and General Arrangem | RFA-MEP-GN | Approved | High | 2026-02-16 | 2026-02-09
008 | Precasst R.C. Chamber Ring & Precast Inspection C | RFA-MEP-MAT | Approved with comments | High | 2025-07-25 | 2025-07-11
003 | material submission of underground sanitary upvc | RFA-MEP-MAT | Approved | High | 2025-07-14 | 2025-07-11
001 | submission of lightning protection system shop dra | RFA-MEP-DWG | Approved with comments | High | 2025-06-27 | 2025-06-13
001 | Request for approval of materials for Undergroun | RFA-MEP-MAT | Approved | High | 2025-07-10 | 2025-06-26
009 | Cast Iron Gully Trap | RFA-MEP-MAT | Approved with comments | High | 2025-07-29 | 2025-07-15
010 | Hydrant Pillar and Ductile Iron Valve Box Cover & | RFA-MEP-MAT | Approved with comments | High | 2025-08-14 | 2025-07-31 |  | Please submit the test report to confirm the valve box cover pass the SS EN 124.
006 | Ductile Iron Water Pipe & Fittings | RFA-MEP-MAT | Approved | High | 2025-07-24 | 2025-07-10
007 | Underground Drainage uPVC Pipe & Fittings | RFA-MEP-MAT | Approved | High | 2025-07-24 | 2025-07-10
004 | Lightning Protection System Fittings & Accessories | RFA-MEP-MAT | Approved | High | 2025-07-14 | 2025-06-30
019 | sprinkler pipes and dry riser pipes | RFA-MEP-MAT | Approved with comments | High | 2025-10-16 | 2025-10-09 |  | Please use Galvanised heavy grade for dry riser and Galvanised medium grade for hosereel. Please use black steel pipe minimum medium grade for sprinkler pipe.
005 | Grease Trap (Brand : Eneka) | RFA-MEP-MAT | Approved with comments | High | 2025-07-15 | 2025-08-02
013 | Ductile Iron Heavy Duty Telecom Manhole Cover ( B | RFA-MEP-MAT | Approved with comments | High | 2025-08-25 | 2025-08-11 |  | Please submit certification of SS30 grade A1 and B.
016 | FIRE RATED DUCT BOARD | RFA-MEP-MAT | Approved with comments | Normal | 2025-10-11 | 2025-09-27
018 | PVC CONDUIT AND ACCESSORIES | RFA-MEP-MAT | Approved | High | 2025-10-13 | 2025-10-06
032 | PEX Pipe and Fittings | RFA-MEP-MAT | Approved | High | 2025-11-06 | 2025-10-30
009 | Sanitary system details_ Parts of 1st Storey Plan | RFA-MEP-DWG | Approved with comments | High | 2025-09-15 | 2025-11-03
022 | 3rd storey sanitary system | RFA-MEP-DWG | Approved with comments | Normal | 2025-11-17 | 2025-11-03
051 | Electrical - 300 KVA Genset | RFA-MEP-MAT | Approved with comments | High | 2025-11-10 | 2025-11-02 |  | Please refer to the attachment.
050 | Electrical Pipe for Underground Work | RFA-MEP-MAT | Approved with comments | High | 2025-11-10 | 2025-11-02 |  | Please refer to the attachment.
049 | Electrical - Lightning Protection System Material | RFA-MEP-MAT | Approved with comments | High | 2025-11-10 | 2025-11-02 |  | Refer to the attachment and comment.
047 | Electrical - PWD (EVC - Switch and Control Panel) | RFA-MEP-MAT | Approved with comments | High | 2025-11-10 | 2025-11-02 |  | Please refer to the attachment for the comments.
035 | Aircon Drain pipe | RFA-MEP-MAT | Approved with comments | High | 2025-11-08 | 2025-11-01 |  | Please refer to attachment for comment.
034 | uPVC Trunking for AC Installation | RFA-MEP-MAT | Approved | High | 2025-11-08 | 2025-11-01
017 | closed-cell Insulation for air con drainage pipe | RFA-MEP-MAT | Approved | High | 2025-10-11 | 2025-10-04
023 | DFMA MEP modules layout plan and DFMA MEP Vertica | RFA-MEP-DWG | Approved with comments | High | 2025-11-18 | 2025-12-01
012 | Precast Telecom Manhole | RFA-MEP-MAT | Approved | High | 2025-08-21 | 2025-08-29
080 | Conduit (Fire Protection Service) | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-11-18 |  | Please use class 4 for surface mounted conduit.
079 | Trunking (Fire Protection Service) | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-11-18
061 | Typical plan & Elevation for Future Refrigerant P | RFA-MEP-DWG | Approved | High | 2026-03-28 | 2026-03-14
043 | NRD VCD | RFA-MEP-MAT | Approved with comments | High | 2025-11-08 | 2025-11-01 |  | Please refer to the attachment for comment.
012 | SPPG drawpits Type 3 plan , section and detail | RFA-MEP-DWG | Approved | High | 2025-09-27 | 2025-10-02
015 | Aircon drain pipe 1st Storey Layout plan & section | RFA-MEP-DWG | Approved | High | 2025-10-02 | 2025-10-07
001 | Method of Statement for installation of undergrou | RFA-MEP-MS | Approved with comments | High | 2025-09-02 | 2025-11-13
022 | BUTTERFLY VALVE | RFA-MEP-MAT | Approved | Normal | 2025-10-30 | 2025-10-16
014 | uPVC Pipes & Fittings, SS213 | RFA-MEP-MAT | Approved | High | 2025-09-19 | 2025-09-05
013 | Sprinkler/Hydrant Tank & Pump Room Detail | RFA-MEP-DWG | Approved with comments | High | 2025-10-04 | 2026-02-05
003 | 1st storey sanitary system shop drawing submission | RFA-MEP-DWG | Approved with comments | High | 2025-07-28 | 2025-09-26
015 | JET FAN | RFA-MEP-MAT | Approved with comments | Normal | 2025-10-11 | 2025-09-27 |  | Please submit the simulation layout for the jet fan and MV fan with relevant calculation.
056 | 7th to 9th storey plumbing system | RFA-MEP-DWG | Approved with comments | High | 2026-03-07 | 2026-02-21
082 | Screen Cable | RFA-MEP-MAT | Approved with comments | Normal | 2025-12-01 | 2025-11-18 |  | Please refer to attachment.
048 | Plumbing system layout- canteen toilet details | RFA-MEP-DWG | Approved | High | 2026-02-02 | 2026-01-19
069 | Fireman Intercom | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2026-01-22
028 | 2nd Storey MV layout plan | RFA-MEP-DWG | Approved with comments | High | 2025-12-15 | 2025-12-03
078 | FR Cable | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-11-16
037 | Cable Layout Plan 1st Storey Cable Routing Layout | RFA-MEP-DWG | Approved with comments | High | 2026-01-02 | 2025-12-19
005 | Method of Statement for Pipe Installation Throu | RFA-MEP-MS | Approved with comments | High | 2025-11-26 | 2025-11-21
037 | Thermal Insulation for Aircon Refri and Drain Pipe | RFA-MEP-MAT | Approved with comments | High | 2025-11-08 | 2025-11-01 |  | Refer to attachment for comment
038 | ACMV - FR Cable | RFA-MEP-MAT | Approved with comments | High | 2025-11-08 | 2025-11-01 |  | Please refer to attachment for comment.
008 | Fire Hydrant System 1st Storey Layout Plan | RFA-MEP-DWG | Approved with comments | High | 2025-09-11 | 2025-11-29
005 | submission of SPPG drawpits Type 1 &2 plan , sect | RFA-MEP-DWG | Approved with comments | High | 2025-08-07 | 2025-10-27
027 | Aircon Unit (For FCC) | RFA-MEP-MAT | Approved | High | 2025-11-06 | 2025-11-10
016 | SPPG drawpits Type 4 &5 plan , section and detail | RFA-MEP-DWG | Approved with comments | High | 2025-10-14 | 2025-10-25
020 | GALVANISED SHEET STEEL | RFA-MEP-MAT | Approved | High | 2025-10-27 | 2025-11-10
083 | Busduct | RFA-MEP-MAT | Approved | Normal | 2025-12-12 | 2025-11-28
084 | LV Cable | RFA-MEP-MAT | Approved | Normal | 2025-12-12 | 2025-11-28
085 | Switches and Isolator | RFA-MEP-MAT | Approved | Normal | 2025-12-12 | 2025-11-28
044 | MV layout plan @ Roof | RFA-MEP-DWG | Approved | High | 2026-01-19 | 2026-01-05
029 | Thermal Insulation (Rockwool) for ACMV Work | RFA-MEP-MAT | Approved with comments | High | 2025-11-06 | 2025-10-30 |  | Please refer the attachment.
055 | Flow Switch | RFA-MEP-MAT | Approved | Normal | 2025-11-28 | 2025-11-15
066 | Manual Call Point | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-11-16
073 | Fire Extinguisher | RFA-MEP-MAT | Approved | High | 2025-11-30 | 2025-11-16
060 | Standby Hose | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-11-16 |  | Please refer to consultant comment.
063 | Hosereel Cabinet | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-11-16 |  | Please refer to attachment.
065 | Smoke Detector | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-11-16
010 | Sanitary system details of Gully Trap | RFA-MEP-DWG | Approved | High | 2025-09-15 | 2025-11-03
014 | 1st storey ACMV layout plan & section drawings | RFA-MEP-DWG | Approved with comments | High | 2025-10-07 | 2025-12-09
017 | 2nd storey sanitary system layout shop drawing | RFA-MEP-DWG | Approved with comments | High | 2025-10-21 | 2025-11-18
026 | Electrical Installation Underground Layout 1st St | RFA-MEP-DWG | Approved with comments | High | 2025-11-26 | 2025-11-19
029 | 3rd Storey MV layout plan | RFA-MEP-DWG | Approved with comments | High | 2025-12-15 | 2025-12-01
030 | 10th Storey MV layout plan | RFA-MEP-DWG | Approved with comments | Normal | 2025-12-15 | 2025-12-09
062 | Hosereel Drum | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-11-16 |  | Refer to comment.
068 | Fire Alarm Bell | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-11-16
067 | Strobe Light | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-11-16
064 | Fire Alarm Panel | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-11-16
113 | Dry Horizontal Sidewall Sprinkler | RFA-MEP-MAT | Approved | High | 2026-01-26 | 2026-01-20
051 | 2nd Storey Cable Routing Layout | RFA-MEP-DWG | Approved with comments | High | 2026-02-11 | 2026-01-28
062 | Plumbing Reticulation System Schematic Diagram | RFA-MEP-DWG | Approved with comments | High | 2026-04-03 | 2026-03-20
007 | Method of Statement for Above ground Plumbing an | RFA-MEP-MS | Approved with comments | Normal | 2026-02-17 | 2026-03-18
046 | ACMV elevations | RFA-MEP-DWG | Approved | High | 2026-01-26 | 2026-01-12
090 | Brass Check Valve for Plumbing Service | RFA-MEP-MAT | Approved | Normal | 2025-12-13 | 2025-11-29
091 | DI Check Valve for Plumbing Service | RFA-MEP-MAT | Approved | Normal | 2025-12-13 | 2025-11-29
092 | Brass Gate Valve for Plumbing Service | RFA-MEP-MAT | Approved | Normal | 2025-12-13 | 2025-11-29
002 | submission of lifts' shop drawings | RFA-MEP-DWG | Approved | High | 2025-07-18 | 2026-01-08
027 | 200 Ǿ Opening For 150 Ǿ Dry Riser Pipe at FFL 5 Le | RFA-MEP-DWG | Approved with comments | High | 2025-12-12 | 2025-12-01
071 | Copper Earth Rod and Tape (Fire Protection Service | RFA-MEP-MAT | Approved | Normal | 2025-11-30 | 2025-12-24
054 | Alarm Gong | RFA-MEP-MAT | Approved | Normal | 2025-11-28 | 2025-12-24
053 | Ductile Fitting for Fire Protection Service | RFA-MEP-MAT | Approved | Normal | 2025-11-28 | 2025-12-24
093 | DI Gate Valve for Plumbing and Hydrant Piping | RFA-MEP-MAT | Approved with comments | Normal | 2025-12-13 | 2025-11-29 |  | Noted on the change of brand from original proposed brand (Norika) during tender stage. No objection on the proposed brand.
025 | 2nd Storey Plumbing System | RFA-MEP-DWG | Approved with comments | High | 2025-12-01 | 2025-12-20
038 | 4th storey sanitary system | RFA-MEP-DWG | Approved with comments | High | 2026-01-02 | 2025-12-19
097 | PRV | RFA-MEP-MAT | Approved with comments | Normal | 2025-12-15 | 2025-12-22 |  | Please refer to attachment.
039 | 5th to 09th typical storey sanitary system | RFA-MEP-DWG | Approved with comments | High | 2026-01-02 | 2025-12-19
070 | Earth Pit | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-12-24 |  | Please refer to the attachment.
052 | Ductile Iron Pipe for Fire Protection | RFA-MEP-MAT | Approved | Normal | 2025-11-28 | 2025-12-24
024 | Mechanical Fittings | RFA-MEP-MAT | Approved with comments | High | 2025-11-10 | 2025-12-24 |  | Refer to attachment.
077 | PVC Cable (Fire Protection Services) | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2025-12-24 |  | Refer comment.
036 | AC Copper Pipe | RFA-MEP-MAT | Approved | High | 2025-11-08 | 2025-12-23
021 | Hollow Core Drilling Point for DfMA MEP Module | RFA-MEP-DWG | Approved with comments | High | 2025-11-17 | 2025-11-28
041 | Silicon Sealant | RFA-MEP-MAT | Approved | High | 2025-11-08 | 2025-12-23
1 | Proposed Services Pipes/Tray/Trunking/Conduit Fini | RFA-MEP-GN | Approved with comments | High | 2025-11-26 | 2025-12-27 |  | Refer to attachment.
042 | ACMV Louvre and Grill | RFA-MEP-MAT | Approved with comments | High | 2025-11-08 | 2025-12-27 |  | Please refer to attachment for comments.
031 | Aircon drain pipe 2nd Storey Layout plan & sectio | RFA-MEP-DWG | Approved with comments | High | 2025-12-20 | 2025-12-06
058 | BI Cabinet | RFA-MEP-MAT | Approved | Normal | 2025-11-28 | 2025-12-23
116 | Hosereel Water Tank | RFA-MEP-MAT | Approved with comments | Normal | 2026-03-18 | 2026-03-04
101 | Lamp Post (Level 1 Entry and Level 10) | RFA-MEP-MAT | Approved | Normal | 2025-12-29 | 2025-12-15
108 | DfMA Channel Frame | RFA-MEP-MAT | Approved with comments | Normal | 2026-01-22 | 2026-01-08 |  | Please refer to the attachment for the comments.
063 | 1st Storey Sanitary System- Last IC Part Plan-01 | RFA-MEP-DWG | Approved with comments | High | 2026-04-02 | 2026-03-26
045 | COMBINED SERVICES DRAWING 1ST STOREY TYPICAL UNIT | RFA-MEP-DWG | Approved with comments | High | 2026-01-21 | 2026-01-07
103 | Single Cable for Lift | RFA-MEP-MAT | Approved with comments | Normal | 2026-01-06 | 2025-12-30 |  | Please refer to attachment for comment.
102 | Conduit and Accessories for Electrical Concealed a | RFA-MEP-MAT | Approved | Normal | 2026-01-05 | 2025-12-22
105 | PVC Cable for Lift Installation | RFA-MEP-MAT | Approved | Normal | 2026-01-14 | 2025-12-31
104 | Trunking for Lift Installation Work | RFA-MEP-MAT | Approved | Normal | 2026-01-06 | 2025-12-31
040 | ACMV - Control Panel Component | RFA-MEP-MAT | Approved with comments | High | 2025-11-08 | 2025-12-27 |  | Please refer to attachment for comment.
112 | Biometric Face Recognition and Card Access System | RFA-MEP-MAT | Approved with comments | Normal | 2026-02-02 | 2026-01-20 |  | Please refer to the attachment for comments.
120 | Light Fitting Cut Sheet (Part 2) | RFA-MEP-MAT | Approved with comments | Normal | 2026-05-14 | 2026-04-29
086 | Emergency and Exit Light | RFA-MEP-MAT | Approved with comments | Normal | 2025-12-12 | 2026-04-29
046 | Electrical Cable Containment System | RFA-MEP-MAT | Approved with comments | High | 2025-11-08 | 2026-04-28
032 | 3rd storey plumbing system | RFA-MEP-DWG | Approved | High | 2025-12-31 | 2026-01-08
011 | 1st Storey Plumbing System | RFA-MEP-DWG | Approved with comments | High | 2025-09-16 | 2026-01-09
047 | Plumbing system details -part of 1st and 2nd store | RFA-MEP-DWG | Approved with comments | High | 2026-01-26 | 2026-01-12
033 | DfMA MEP Vertical Module Framing Details | RFA-MEP-DWG | Approved with comments | High | 2025-12-31 | 2025-12-17
041 | submission of DFMA MEP horizontal module typical | RFA-MEP-DWG | Approved with comments | High | 2026-01-07 | 2025-12-24
057 | Electrical Riser Details Layout | RFA-MEP-DWG | Approved with comments | High | 2026-03-09 | 2026-02-23
078 | Plumbing System- Water Riser Detail Plan and Elev | RFA-MEP-DWG | Approved with comments | Normal | 2026-05-01 | 2026-04-17
050 | 1st storey electrical power layout | RFA-MEP-DWG | Approved with comments | High | 2026-02-05 | 2026-01-22
087 | roof plan sanitary system | RFA-MEP-DWG | Approved with comments | High | 2026-05-16 | 2026-05-02
079 | 3rd storey combined services drawings plan and se | RFA-MEP-DWG | Approved with comments | High | 2026-05-11 | 2026-04-27
060 | ACMV equipment schedules | RFA-MEP-DWG | Approved with comments | High | 2026-03-26 | 2026-03-12
081 | Lighting Layout typical 3rd storey to 9th storey | RFA-MEP-DWG | Approved with comments | High | 2026-05-15 | 2026-04-30
087 | Light Fitting for ESS and MDF Rooms | RFA-MEP-MAT | Approved with comments | Normal | 2025-12-12 | 2026-02-11 |  | Refer to attachment
008 | Method of Statement for Delivery and Installati | RFA-MEP-MS | Approved with comments | High | 2026-02-28 | 2026-02-14
117 | Polymer Concrete Jacking Pipe (MI) | RFA-MEP-MAT | Approved | Normal | 2026-04-20 | 2026-04-06
085 | 7TH TO 9TH STOREY ELV LAYOUT | RFA-MEP-DWG | Approved with comments | High | 2026-05-16 | 2026-05-02
3 | Drop in Anchor and Support System for Fire Protect | RFA-MEP-GN | Approved | High | 2026-01-13 | 2026-02-19
028 | Fire Stop Material for ACMV Work | RFA-MEP-MAT | Approved with comments | High | 2025-11-06 | 2026-04-20
4 | Drop in Anchor and Support System for Electrical S | RFA-MEP-GN | Approved with comments | High | 2026-01-13 | 2026-05-14
053 | COMBINED SERVICES DRAWING 2ND TO 9TH STOREY TYPIC | RFA-MEP-DWG | Approved with comments | High | 2026-02-20 | 2026-03-17
030 | Fire Damper | RFA-MEP-MAT | Approved with comments | High | 2025-11-06 | 2026-04-08
003 | Method of Statement for Fire Protection Instal | RFA-MEP-MS | Approved with comments | High | 2025-11-27 | 2026-02-14
8 | Proposed MV Louvre color for Installation at Exter | RFA-MEP-GN | Approved with comments | High | 2026-04-14 | 2026-04-14
077 | Sprinkler Layout , Fire Alarm, Hose Reel, Dry Rise | RFA-MEP-DWG | Approved with comments | High | 2026-05-01 | 2026-04-17
019 | Sprinkler Layout-1st Storey Plan | RFA-MEP-DWG | Approved | High | 2025-10-31 | 2026-04-04
020 | 1st Storey Plan Fire Alarm, Hosereel, Dry Riser & | RFA-MEP-DWG | Approved | High | 2025-11-01 | 2026-04-04
034 | Fire Protection System Installation Detail | RFA-MEP-DWG | Approved with comments | High | 2026-01-01 | 2026-04-11
067 | 2nd storey electrical power layout | RFA-MEP-DWG | Approved with comments | High | 2026-04-27 | 2026-04-13
036 | Sprinkler Layout , Fire Alarm, Hose Reel, Dry Rise | RFA-MEP-DWG | Approved with comments | High | 2026-01-02 | 2026-04-11
070 | Automatic Fire Alarm System Schematic Diagram( Ad | RFA-MEP-DWG | Approved with comments | High | 2026-04-29 | 2026-04-15
7 | Unit DB and Meter Board | RFA-MEP-GN | Approved | High | 2026-02-27 | 2026-04-28
081 | Fire Rated Box-up Material (Fire Rated Box-up) | RFA-MEP-MAT | Approved with comments | Normal | 2025-11-30 | 2026-04-29
043 | Weatherproof 300KVA Genset Enclosure at 10th Store | RFA-MEP-DWG | Approved with comments | High | 2026-01-12 | 2026-04-27
064 | Proposed Dry Riser Location at FFL 4 ( Typical Lev | RFA-MEP-DWG | Approved with comments | High | 2026-04-09 | 2026-03-26
083 | 2nd Storey ELV Layout | RFA-MEP-DWG | Approved with comments | High | 2026-05-14 | 2026-04-30
042 | One Way EVC System | RFA-MEP-DWG | Approved with comments | High | 2026-01-12 | 2026-05-02
110 | Light Fitting Cut Sheet | RFA-MEP-MAT | Approved with comments | Normal | 2026-01-22 | 2026-05-14
072 | Two- Way Emergency Voice Communication System Sc | RFA-MEP-DWG | Approved | High | 2026-04-29 | 2026-04-15
074 | Sprinkler Layout , Fire Alarm, Hose Reel, Dry Rise | RFA-MEP-DWG | Approved with comments | High | 2026-04-30 | 2026-04-16
068 | 3rd to 9th storey electrical power layout ( typica | RFA-MEP-DWG | Approved | High | 2026-04-27 | 2026-04-13
024 | Lighting Layout 1st storey plan | RFA-MEP-DWG | Approved with comments | High | 2025-11-20 | 2026-04-28
091 | 3rd to 6th Storey Typical Cable Routing Layout | RFA-MEP-DWG | Approved | High | 2026-06-13 | 2026-05-30
080 | Electrical Installation Lighting Layout 2nd Stor | RFA-MEP-DWG | Approved with comments | High | 2026-05-12 | 2026-04-28
075 | Sprinkler Layout , Fire Alarm, Hose Reel, Dry Rise | RFA-MEP-DWG | Approved with comments | Normal | 2026-04-30 | 2026-04-16
086 | 10th storey sanitary system | RFA-MEP-DWG | Approved with comments | High | 2026-05-16 | 2026-05-02
092 | 7th to 9th Storey Typical Cable Routing Layout | RFA-MEP-DWG | Approved with comments | High | 2026-06-13 | 2026-05-30
076 | Sprinkler Layout , Fire Alarm, Hose Reel, Dry Rise | RFA-MEP-DWG | Approved with comments | High | 2026-05-01 | 2026-04-17
073 | Sprinkler Layout , Fire Alarm, Hose Reel, Dry Rise | RFA-MEP-DWG | Approved with comments | High | 2026-04-30 | 2026-04-16
071 | Dry Riser And Hose Reel System Schematic Diagram | RFA-MEP-DWG | Approved | High | 2026-04-29 | 2026-04-15
026 | Mechanical Ventilation Fan | RFA-MEP-MAT | Approved with comments | High | 2025-11-06 | 2026-04-16
035 | Sprinkler Layout , Fire Alarm, Hose Reel, Dry Rise | RFA-MEP-DWG | Approved with comments | High | 2026-01-02 | 2026-04-04
065 | Fire Hydrant System 1st Storey - Part Plan( FH 4/ | RFA-MEP-DWG | Approved with comments | High | 2026-04-21 | 2026-04-07
039 | Power Cable for ACMV System | RFA-MEP-MAT | Approved | High | 2025-11-08 | 2026-04-06
119 | Factory Units Aircon Pipe Sleeve and Endcap | RFA-MEP-MAT | Approved with comments | High | 2026-04-23 | 2026-04-16
090 | Proposed Dry Riser Breeching Inlet Pipes at leve | RFA-MEP-DWG | Approved with comments | High | 2026-06-12 | 2026-05-29
054 | 2nd storey combined services drawings | RFA-MEP-DWG | Approved with comments | High | 2026-02-28 | 2026-05-23
10 | Voltage Drop Calculation | RFA-MEP-GN | Approved | Normal | 2026-05-21 | 2026-05-07
118 | Portable Water Tank | RFA-MEP-MAT | Approved | Normal | 2026-04-28 | 2026-06-06
121 | GI Conduit _ ACMV | RFA-MEP-MAT | Approved | High | 2026-06-13 | 2026-06-06
2 | Drop in Anchor and Support System for Plumbing and | RFA-MEP-GN | Approved | High | 2026-01-12 | 2026-06-10
5 | Drop in Anchor and Support System for ACMV System | RFA-MEP-GN | Approved | High | 2026-01-15 | 2026-06-16

## ChartData (hidden)
Status | Count | Discipline | Total | Approved | Pending | Resubmit
Approved | 156 | MEP | 242 | 212 | 18 | 11
Approved with comments | 212 | Structural | 90 | 76 | 14 | 0
Pending | 37 | Architectural | 87 | 79 | 5 | 3
Revise & Resubmit | 14 | BIM | 1 | 1 | 0 | 0