## Summary
SUBCON vs MODEL — ROLLER SHUTTER COMPARISON
2ND STOREY ¦ Zone 1 (Grids 1-15) ¦ 2026-06-16 09:17
Total |  | ✅ Matched |  | 🔴 Size Issue |  | ❌ Not in Model
15 |  | 12 |  | 3 |  | 0
Sorted: ✅ Matched first → 🔴 Issues last ¦ All 15 doors matched by Type + Grid Reference
Subcon Ref | Type | Subcon Size | Model Size | Subcon Grid | Model Grid | Model Mark | Match | Status | Action
✅ MATCHED (12 doors)
L2-RS-01 | RS1 | 3000x3650 | 3000x3650 | 3-K | 3-K | 427 | EXACT | ✅ OK | —
L2-IFSS240-01 | FRS2 | 3500x3650 | 3500x3650 | 3-I | 3-I | 425 | EXACT | ✅ OK | —
L2-IFSS240-02 | FRS2 | 3500x3650 | 3500x3650 | 4-I | 4-I | 1488 | EXACT | ✅ OK | —
L2-RS-01 | RS5 | 10400x3650 | 10400x3650 | 4/5-K | 4/5-K | 424 | EXACT | ✅ OK | —
L2-RS-02 | RS5 | 10400x3650 | 10400x3650 | 5/6-K | 5/6-K | 392 | EXACT | ✅ OK | —
L2-RS-03 | RS5 | 10400x3650 | 10400x3650 | 6/7-K | 6/7-K | 391 | EXACT | ✅ OK | —
L2-RS-04 | RS5 | 10400x3650 | 10400x3650 | 7/8-K | 7/8-K | 389 | EXACT | ✅ OK | —
L2-RS-05 | RS5 | 10400x3650 | 10400x3650 | 8/9-K | 8/9-K | 383 | EXACT | ✅ OK | —
L2-RS-06 | RS5 | 10400x3650 | 10400x3650 | 9/10-K | 9/10-K | 459 | EXACT | ✅ OK | —
L2-RS-07 | RS5 | 10400x3650 | 10400x3650 | 10/11-K | 10/11-K | 372 | EXACT | ✅ OK | —
L2-RS-08 | RS5 | 10400x3650 | 10400x3650 | 11/12-K | 11/12-K | 377 | EXACT | ✅ OK | —
L2-RS-02 | RS1 | 3000x3650 | 3000x3650 | 12-K | 12-K | 359 | EXACT | ✅ OK | —
🔴 SIZE ISSUES (3 doors)
L2-IFSS240-01 | FRS4 | 7050x3650 | 6800x3650 | 2/3-I | 2/3-I | 1487 | EXACT | SIZE 7050x3650→6800x3650 | Verify size with consultant (+250mm)
L2-RS-01 | RS4 | 7100x3650 | 7075x3650 | 3/4-K | 3/4-K | 456 | EXACT | SIZE 7100x3650→7075x3650 | Check model — size diff 25mm vs correct 7075mm
L2-IFSS240-01 | FRS5 | 9150x3650 | 8875x3650 | 4/5-I | 4/5-I | 1489 | EXACT | SIZE 9150x3650→8875x3650 | Verify size with consultant (+275mm)

## Matched
✅ MATCHED (Type + Size + Grid)
Zone 1 ¦ 12/15 matched
Subcon Ref | Type | Subcon Size | Model Size | Subcon Grid | Model Grid | Model Mark | Match | Status | Action
L2-RS-01 | RS1 | 3000x3650 | 3000x3650 | 3-K | 3-K | 427 | EXACT | ✅ OK | —
L2-IFSS240-01 | FRS2 | 3500x3650 | 3500x3650 | 3-I | 3-I | 425 | EXACT | ✅ OK | —
L2-IFSS240-02 | FRS2 | 3500x3650 | 3500x3650 | 4-I | 4-I | 1488 | EXACT | ✅ OK | —
L2-RS-01 | RS5 | 10400x3650 | 10400x3650 | 4/5-K | 4/5-K | 424 | EXACT | ✅ OK | —
L2-RS-02 | RS5 | 10400x3650 | 10400x3650 | 5/6-K | 5/6-K | 392 | EXACT | ✅ OK | —
L2-RS-03 | RS5 | 10400x3650 | 10400x3650 | 6/7-K | 6/7-K | 391 | EXACT | ✅ OK | —
L2-RS-04 | RS5 | 10400x3650 | 10400x3650 | 7/8-K | 7/8-K | 389 | EXACT | ✅ OK | —
L2-RS-05 | RS5 | 10400x3650 | 10400x3650 | 8/9-K | 8/9-K | 383 | EXACT | ✅ OK | —
L2-RS-06 | RS5 | 10400x3650 | 10400x3650 | 9/10-K | 9/10-K | 459 | EXACT | ✅ OK | —
L2-RS-07 | RS5 | 10400x3650 | 10400x3650 | 10/11-K | 10/11-K | 372 | EXACT | ✅ OK | —
L2-RS-08 | RS5 | 10400x3650 | 10400x3650 | 11/12-K | 11/12-K | 377 | EXACT | ✅ OK | —
L2-RS-02 | RS1 | 3000x3650 | 3000x3650 | 12-K | 12-K | 359 | EXACT | ✅ OK | —

## Issues
🔴 SIZE DISCREPANCIES — ACTION REQUIRED
Zone 1 ¦ 3 issues ¦ Grid refs all matched ✅
Subcon Ref | Type | Subcon Size | Model Size | Subcon Grid | Model Grid | Model Mark | Match | Status | Action
L2-IFSS240-01 | FRS4 | 7050x3650 | 6800x3650 | 2/3-I | 2/3-I | 1487 | EXACT | SIZE 7050x3650→6800x3650 | Verify size with consultant (+250mm)
L2-RS-01 | RS4 | 7100x3650 | 7075x3650 | 3/4-K | 3/4-K | 456 | EXACT | SIZE 7100x3650→7075x3650 | Check model — size diff 25mm vs correct 7075mm
L2-IFSS240-01 | FRS5 | 9150x3650 | 8875x3650 | 4/5-I | 4/5-I | 1489 | EXACT | SIZE 9150x3650→8875x3650 | Verify size with consultant (+275mm)